## Sheet1
e
PROJECT | Building a Generic Configurable UI Gadget for Analytics
DATE | 12/18/2014 - 01/25/2015
MEMBERS | Mohammed Fawsan, Fasna Jifry, Pubudu Dodangoda
STAKEHOLDERS | Srinath Perera, CEP Team
Mile Stone | Task |  | Start Date | Completion Date | Actual Completion Date | State
Assignee(s)
Requirements Gathering and Research
| Gathering the Usecases of the UI Gadget | Fawsan, Fasna, Pubudu | 2014-12-18 | 2014-12-08 |  | Finished
| Understanding the Diagrams & Possible drill downs | Fawsan, Fasna, Pubudu | 2014-12-19 | 2014-12-19 |  | Finished
| Getting started with D3.js | Fawsan, Fasna, Pubudu | 2014-12-22 | 2014-12-23 |  | Finished
MileStone -1 Implementation with Tests
2
| Implementation of Single Number Diagram | Fawsan | 2015-01-05 | 2015-01-07 |  | Finished
| Implementation of Line Chart | Pubudu | 2015-01-05 | 2015-01-07 |  | Finished
| File handling and Data Conversion | Fasna | 2015-01-05 | 2015-01-07 |  | Finished
| Testing the data compatability for implemented diagrams (Categorical & Numerical Data) | Fawsan, Fasna, Pubudu | 2015-01-07 | 2015-01-09 |  | Finished
MileStone -2 Implementation with Tests
3
| Implementation of Table | Fawsan | 2015-01-12 | 2015-01-14 |  | Finished
| Implementation of Group Bar | Fasna | 2015-01-12 | 2015-01-14 |  | Finished
| Implementation of Map | Pubudu | 2015-01-12 | 2015-01-14 |  | Finished
| Testing the data compatability for implemented diagrams (Categorical & Numerical Data) | Fawsan, Fasna, Pubudu | 2015-01-14 | 2015-01-16 |  | Finished
MileStone -3 Design, Implementation & Testing | Finalizing the Diagrams
4
| Adding all the necessary components to the diagrams | Fawsan, Fasna, Pubudu | 2015-01-19 | 2015-01-19 |  | Finished
| Adding Styles to the diagrams | Fawsan, Fasna | 2015-01-20 | 2015-01-20 |  | Finished
| Test the diagrams for different data sets | Fasna, Pubudu | 2015-01-21 | 2015-01-21 |  | Finished
MileStone-4 Testing | Finalizing the Gadget
| Adding filters to the diagrams | Fawsan, Fasna, Pubudu | 2015-01-22 | 2015-01-23 |  | Finished
Testing & Documentation
| Final Code Review |  | 2015-12-03 | 2015-12-03 |  | Finished